## IMPORTANT
Français | [5 empty] | ENGLISH
Before all, read carefully the return date of the required forms and documents. Fill the forms of this file and send it to: amandine.gueurce@planete-sciences.org
FALSE | [5 empty] | TRUE
PLANNING
MINI-ROCKETS
| To be returned before: | December 31st 2011 | January 27th 2012 | March17th 2012 | June 2nd 2012
| Registration | X
| Definition |  | X
Technical File
| Progress_mini-rocket |  | X | X | X
Progress_fusex
| Derogation |  |  | X
EXPERIMENTAL ROCKETS
| To be returned before: | December 31st 2011 | January 27th 2012 | March17th 2012 | June 2nd 2012
| Registration | X
| Definition |  | X
| Technical File |  |  | X | X
Progress_mini-rocket
| Progress_fusex |  | X | X | X
| Derogation |  |  | X
BALLOONS
| To be returned before: | December 31st 2011 | January 27th 2012 | March17th 2012 | June 2nd 2012
| Registration | X
| Definition |  | X
| Technical File | 2 months before lift-off
Progress_mini-rocket
Progress_fusex
| Derogation |  |  | X
HOW TO FILL THESES FORMS ?
Cells with a proposed selection are highlighted like this: |  |  |  |  | Select...
Some cells are filled automatically based on previous selections or inputs
A list of the required documents is included at the end of the forms
V02.10.11

## 1-Déclaration
2011-2012
FICHE DE DECLARATION DE PROJET ESPACE
A retourner avant le 31 décembre 2011
UNE FICHE PAR PROJET
Cette fiche est nécessaire à toute inscription pour la session Espace de l'année mentionnée ci-dessus.
Elle accompagne l'adhésion Planète Sciences ainsi que le "Contrat Projet Espace". Seul ce contrat, passé entre le Club,
le CNES et Planète Sciences tient lieu d'engagement pour chacune des parties et ce durant toute la session en question.
Nom du Projet
Type de projet | Sélectionner …
VOTRE CLUB
NOM
Adresse postale
Téléphone
Email
Site Web | http://
VOTRE RESPONSABLE
NOM
Adresse postale
Téléphone fixe
Téléphone mobile
Email
EXPERIENCES ENVISAGEES
1-
2-
3-
4-
LANCEMENT OU LACHER : dates et lieux souhaités
* obligatoire pour les fusées expérimentales et projet spéciaux
Manifestation | Sélectionner …
Lieu
Date
Remarques ou demandes particulières
Propulseur | Sélectionner …
Emetteur | Sélectionner …
LE CLUB
Quelques mots sur la vie du club et de ses membres : historique, organisation, fonctionnement, réunions, moyens financiers et matériel…
PARTICIPANTS identifiés à ce jour
5 membres minimum pour les projets expérimentaux - 2 pour les minifs
Veuillez joindre à ce dossier de projet une photo de l'équipe que nous afficherons en ligne sur notre site web
Responsable de projet
Nom - Prénom
Age
Email
Tél
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 1
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 2
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 3
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 4
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 5
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 6
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 7
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 8
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 9
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 10
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 11
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 12
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 13
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 14
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 15
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 16
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 17
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 18
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures
Membre 19
Nom - Prénom
Age
Email
Niveau d'études
Compétences
Réalisations antérieures
Membre 20
Nom - Prénom
Age
Email
Niveau d'études
Compétences | Sélectionner …
Réalisations antérieures

## 1-Registration
2011-2012
SPACE DIVISION - PROJECT REGISTRATION FORM
To be returned before December 31st 2011
ONE FORM PER PROJECT
This form must be filled to register for a project for the space division period mentioned here above.
It has to be returned with your membership to Planète-Sciences as well as the « Space Project Contract »
This contract, filled by the club, Planète-Sciences and CNES, is the only engagement between all parties during the period above mentioned.
Project name | Single stage rocket with autonomous recovery guidance system by Parafoil
Type of project | Experimental rocket
YOUR CLUB
NAME | Kyutech (Kyushu Institute of Technology) Space Club
Address | Kyushu Institute of Technology, Department of Mechanical and Ccntrol Enginering, Space Engineering Course 1-1 Sensui, Tobata, Kita-kyushu, Fukuoka 804-8550 Japan
Phone | +81-(0)93-884-3179
Email | yonemoto@mech.kyutech.ac.jp
Web site | http://
YOUR LEADER
NAME
Address
Fixed phone
Mobile phone
Email
PLANNED EXPERIMENTS
1- | Land within 100 meters of target by autonomous recovery guidance system
2- | Roll control by aerodynamic fins
3- | Measurement of flight data (speed, altitude and air route)
4- | Video recording for attitude control validation
LAUNCH OR LIFT-OFF: wishes for date and place
* mandatory for the experimental rockets and the special projects
Event | National campaign*
Place | Biscarosse
Date
Remarks or specific requests
Propellor type | Orignal (Pro75-3G)
Transmitter type | Kiwi Millenium
THE CLUB
Tell us about your club and its members : history, organisation, functioning, meetings, fundings, equipments…
kyutech Space Club was founded in December, 2005 as a space engineering club of students who are studying at Kyushu Institute of Technology that located at Kyushu District of Southern Japan. We have successfully launched a rocket break the sound barrier in 2010. The goal of this club is to make the rocket land for the target within 100 meters. The regular meeting is held every week to inform the project status. Not only the member but also the student who participated in C'space and the supervisor participate in the meeting. And by listening to other staff reports their problems can be shared by all members. The rocket launch project leaded by Kyutech Space Club is funded not only by University, but also supported by graduate student's organization and industries who are interested in such kind of challenges. We can use the necessary tools, manufacturing machines and test sites for the production of rockets.
MEMBERS known at present
A minimum of 5 members is required for experimental projects - 2 for mini-rockets
Club Leader
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 1
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 2
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 3
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 4
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 5
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 6
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 7
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 8
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 9
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 10
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 11
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 12
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 13
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 14
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 15
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 16
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 17
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 18
Last name - First name
Age
Email
Education level
Main skill
Previous project
Member 19
Last name - First name
Age
Email
Education level
Main skill
Previous project
Membre 20
Last name - First name
Age
Email
Education level
Main skill
Previous project

## 2-Définition
2011-2012
FICHE DE DEFINITION ESPACE
A retourner avant le 27 janvier 2012
UNE FICHE PAR PROJET
Cette fiche permet de définir votre projet espace. Elle sera examinée et complétée lors de la 2ème RCE.
La revue de définition est un travail nécessaire afin de commencer la réalisation technique de votre projet dans de bonnes conditions.
Nom du projet
Nom du club
VOTRE PROJET
Type de projet | Sélectionner …
Type de propulseur | Sélectionner …
EXPERIENCE
Un projet expérimental dont la ou les expérience(s) principale(s) ne fonctionne(nt) pas, ne peut être mis en œuvre
L'expérience secondaire est facultative. Votre projet peut ne comporter qu'une ou plusieurs expérience(s) principale(s).
Ne renseignez pas cette partie si votre projet est une fusée sans expérience embarquée.
Expérience(s) principale(s)
Paramètre(s) physique à étudier (précisez les unités)
Pour chacun des paramètres, indiquez la plage de variation attendue
Expérience(s) secondaire(s) (facultatif)
Paramètre(s) physique à étudier (précisez les unités)
Pour chacun des paramètres, indiquez la plage de variation attendue
Paramètre(s) effectivement mesuré(s) (précisez les unités)
Capteur(s) mis en œuvre
Indiquez les formules de conversion
Moyen de sauvegarde des données |  | Enregistrement à bord | FALSE
|  | Réception au sol | FALSE
TELEMESURE
Ne renseignez cette partie que si vous envisagez l'utilisation d'un émetteur dans de votre projet.
* Ce mode est utilisé pour transmettre plus de 4 signaux analogiques. Chaque signal est compris entre 0 et 5V
** Cochez cette case si vous envisagez l'utilisation d'une fréquence nécssitant une licence radio-amateur
Indiquez l'émetteur principal utilisé |  | Sélectionner …
Licence radio-amateur** |  |  | FALSE
Indiquez le type de la télémesure |  | Sélectionner …
Envisagez-vous de faire votre propre logiciel pour décoder votre télémesure ? |  | Sélectionner …
Prévoyez-vous d'autre(s) source(s) d'émission ? |  | Sélectionner …
SYSTEME DE RECUPERATION
Indiquez le type de système de ralentisseur prévu |  | Sélectionner …
Indiquez le type de séparation que vous comptez utiliser |  | Sélectionner …
Indiquez les systèmes utilisés pour mettre en œuvre votre séparation et déployer votre ralentisseur (plusieurs choix possibles) |  | Jack | FALSE | Ventouse magnétique | FALSE
|  | Minuterie | FALSE | Inflammateur | FALSE
|  | Servo-Moteur | FALSE | Vérin pneumatique | FALSE
|  | Autre (précisez) | FALSE
MECANIQUE
Cette partie concerne seulement les fusées, pas les ballons.
Combien d'ailerons comportera votre projet
Quelle partie de la fusée reprend les efforts de la poussée ? |  |  | Sélectionner …
INFORMATIQUE
Renseignez cette partie seulement si vous pensez utiliser un ou plusieurs microcontrolleur(s) dans votre projet.
Y-a-t-il de l'informatique embarquée ? |  | Sélectionner …
SECURITE
* On entend par système pyrotechnique, tout système autre qu'un inflammateur Davey-Bickford.
Utiliserez-vous des systèmes pyrotechniques* dans votre fusée ? |  |  | Sélectionner …
Utiliserez-vous des systèmes pneumatiques dans votre fusée ? |  |  | Sélectionner …
Utiliserez-vous un ou plusieurs fumigène(s) dans votre fusée ? |  |  | Sélectionner …
RESUME DES BESOINS MATERIEL
Propulseur | Sélectionner …
Emetteur | Sélectionner …
Autres
COMMENTAIRES
Cette partie est réservée à Planète Sciences pour y faire des remarques concernant votre projet
Y aura-t-il une demande de dérogation au Cahier des Charges ? |  |  |  | Sélectionner …
Ce projet est-il spécial ? |  |  |  | Sélectionner …
Un dossier de sécurité est-il demandé ? |  |  |  | Sélectionner …

## 2-Definition
2011-2012
SPACE DIVISION - PROJECT DEFINITION FORM
To be returned before January 27th 2012
ONE FORM PER PROJECT
This form is used to technically describe your project. It will be analysed and completed during the second Space Clubs gathering
The definition review is necessary to start in good conditions with the technical development of your project.
Project name | Single stage rocket with autonomous recovery guidance system by Parafoil
Club name | Kyutech (Kyushu Institute of Technology) Space Club
YOUR PROJECT
Type of project | Experimental rocket
Type of propellor | Orignal (Pro75-3G)
EXPERIMENT
An experimental project for which the main(s) experiment(s) is (are) not functionning can't be set up.
The secondary experiment is optional. Your project may contain a single or several main experiment(s)
Do not fill this part if your project is a rocket without onboard experiment
Main experiment(s) |  | Experimental rocket with autonomous recovery guidance system by Parafoil
Parameter(s) to measure (mention the units) |  | Flight Direction
For each parameter, precise the expected result |  | Land at target point using onboard navigation, guidance and control system
Secondary experiment(s) (optional) |  | Not decided
Parameter(s) to measure (mention the units)
For each parameter, precise the expected result
Parameter(s) actually sensed (mention the units)
Sensor(s) involved |  | GPS, Digital compass, Differential pressure (pitot+pressure sensor), IMU
Mention here the data conversion formulae |  | GPS and digital compass information acquisition, pitot pressure(total and static) measurement, integration of angular velocities
Data storage medium |  | Onboard recording | TRUE
|  | Ground reception | TRUE
TELEMETRY
Fill this section only if you plan to make use of a transmitter for your project
* This mode is dedicated to the transmission of more than 4 analog signals. The range for each signal is 0 to 5V
** Check this box in case if you plan to make use of a frequency requiring a radio-amateur licence
Main transmitter involved |  | Kiwi Millenium
Radio-amateur Licence** |  |  | FALSE
Precise the type of telemetry |  | Analog on Kiwi Millenium*
Do you plan to develop your own software tool for telemetry decoding ? |  | No
Do you plan for any other source of emission ? |  | No
RECOVERY SYSTEM
Precise the type of recovery system you plan to set up |  | Other (precise)
Precise the type of ejection you plan to set up |  | Lateral door
Precise which system you plan to set up in order trigger and to eject your recovery system ? (several choices allowed) |  | Plug | TRUE | Magnection suction | FALSE
|  | Timer | TRUE | Igniter | FALSE
|  | Servo-Motor | TRUE | Pneumatic jack | FALSE
|  | Other (precise) | TRUE
MECHANICS
This section deals only with rockets. Skip it in case of Balloon.
Number of fins |  |  | 4
What part of the rocket is bearing the thrust efforts ? |  |  | Internal structure
ONBOARD PROCESSING
Fill this section only if your project includes one or more microcontroler(s)
Any onboard processor or controler ? |  | Yes
Precise their number : |  | Not decided
Precise their usage: |  | Navigation Information Acquisition and NGC Calculation to Command Actuators and Telemetry transmission
SAFETY
*Pyrotechnic system is understood as any other igniter than Davey-Bickford type.
Do you plan to make use of pyrotechnics* systems onboard ? |  |  | No
Do you plan to make use of pneumatics systems onboard ? |  |  | No
Do you plan to make use of one or several fumigatory systems onboard ? |  |  | No
SUMMARY OF MATERIAL REQUIREMENTS
Propellor | Orignal (Pro75-3G)
Transmitter | Kiwi Millenium
Other
COMMENTS
This section is dedicated for comments made by Planete Sciences about your project
Don't miss to plan for a system that will prevent your data from being erased after the flight
Will there be a request for dispensation related to the book of specifications ? |  |  |  | No
Is this a special project ? |  |  |  | No
Is a Risk Analysis requested ? |  |  |  | No

## 3-FicheTechnique
2011-2012
FICHE TECHNIQUE DE PROJET EXPERIMENTAL
A retourner avant le 17 mars 2012 pour les fusées expérimentales
A retourner 2 mois avant la date prévue du lâcher de ballon
UNE FICHE PAR PROJET
Cette fiche est obligatoire pour tout projet expérimental devant être lancé lors de la campagne nationale.
A partir des renseignements saisis dans cette fiche, le CNES et Planète-Sciences valideront la faisabilité technique du projet.
Tous les éléments demandés sont obligatoires. Tout élément manquant peut entraîner un refus de validation du projet.
Les photos de parties de la fusée ou de la fusée elle-même sont bienvenues.
Nom du projet
Nom du club
VOTRE PROJET
Type de projet | Sélectionner …
Type de propulseur | Sélectionner …
EXPERIENCE
Un projet expérimental dont la ou les expérience(s) principale(s) ne fonctionne(nt) pas, ne peut être mis en œuvre
L'expérience secondaire est facultative. Votre projet peut ne comporter qu'une ou plusieurs expérience(s) principale(s).
Ne renseignez pas cette partie si votre projet est une fusée sans expérience embarquée.
Expérience(s) principale(s)
Paramètre(s) physique à étudier (précisez les unités)
Pour chacun des paramètres, indiquez la plage de variation attendue
Expérience(s) secondaire(s) (facultatif) |  | 0
Paramètre(s) physique à étudier (précisez les unités)
Pour chacun des paramètres, indiquez la plage de variation attendue
Paramètre(s) effectivement mesuré(s) (précisez les unités)
Capteur(s) mis en œuvre
Indiquez les formules de conversion
Moyen de sauvegarde des données |  | Enregistrement à bord | FALSE
|  | Réception au sol | FALSE
Y-a-t-il une demande de dérogation au Cahier des Charges ? |  |  | Sélectionner …
Si oui, veuillez joindre la demande de dérogation |  |  | FALSE
TELEMESURE
Ne renseignez cette partie que si vous envisagez l'utilisation d'un émetteur dans de votre projet.
* Ce mode est utilisé pour transmettre plus de 4 signaux analogiques. Chaque signal est compris entre 0 et 5V
** Cochez cette case si vous envisagez l'utilisation d'une fréquence nécssitant une licence radio-amateur
Indiquez l'émetteur principal utilisé |  | Sélectionner …
Licence radio-amateur** |  |  | FALSE
Veuillez joindre une copie de l'autorisation du radio-amateur (si nécessaire) |  |  | FALSE |  | FALSE
Indiquez le type de la télémesure |  | Sélectionner …
Envisagez-vous de faire votre propre logiciel pour décoder votre télémesure ? |  | Sélectionner …
Indiquez l'autonomie
Y-a-t-il d'autre(s) source(s) d'émission |  | Sélectionner …
SYSTEME DE RECUPERATION
Indiquez le type de système de ralentisseur prévu |  | Sélectionner …
Indiquez la vitesse de descente (m/s)
Indiquez le type de séparation que vous comptez utiliser |  | Sélectionner …
Indiquez les systèmes utilisés pour mettre en œuvre votre séparation et déployer votre ralentisseur (plusieurs choix possibles) |  | Jack | FALSE | Ventouse magnétique | FALSE
|  | Minuterie | FALSE | Inflammateur | FALSE
|  | Servo-Moteur | FALSE | Vérin pneumatique | FALSE
|  | Autre (précisez) | FALSE
Indiquez l'autonomie globale du sytème (s)
MECANIQUE
Cette partie concerne seulement les fusées, pas les ballons.
Quelle partie de la fusée reprend les efforts de la poussée ? |  |  | Sélectionner …
Veuillez joindre un schéma général, à l'échelle, de la fusée |  |  | FALSE
Veuillez joindre le plan de la plaque de poussée |  |  | FALSE
STABILITE
Veuillez joindre le fichier trajec de votre fusée (fichier .par) |  |  | FALSE
INFORMATIQUE
Renseignez cette partie seulement si vous pensez utiliser un ou plusieurs microcontrolleur(s) dans votre projet.
Y-a-t-il de l'informatique embarquée ? |  | Sélectionner …
SECURITE
Veuillez joindre les documents techniques et/ou constructeur liés aux systèmes utilisés dans votre fusée.
* On entend par système pyrotechnique, tout système autre qu'un inflammateur Davey-Bickford.
Utilisez-vous des systèmes pyrotechniques* dans votre fusée ? |  |  | Sélectionner …
Utilisez-vous des systèmes pneumatiques dans votre fusée ? |  |  | Sélectionner …
Utilisez-vous un ou plusieurs fumigène(s) dans votre fusée ? |  |  | Sélectionner …
Y-a-t-il un dossier de sécurité ? |  |  | Sélectionner …
Si oui, veuillez joindre le dossier de sécurité |  |  | FALSE
COMMENTAIRES
Cette partie est réservée à Planète Sciences et au CNES pour y faire des remarques techniques concernant votre projet
Planète Sciences
Le schéma général à l'échelle de votre fusée est absent
Le plan de la plaque de poussée est absent
Le fichier .par issu du logiciel Trajec est absent
CNES

## 3-TechnicalFile
2011-2012
TECHNICAL FILE FOR EXPERIMENTAL PROJECT
To be returned before March17th 2012 for experimental rockets
To be returned 2 months prior to the lift-off for the balloons
ONE FORM PER PROJECT
This form is mandatory for any project that has to be set up during the national launching campaign.
From the information contained in this form, CNES and Planète-Sciences will validate the feasibility of your project
All the information requested are manadatory. Any missing information may lead to the validation refusal of the project
Pictures of parts of theproject or the overall project are welcome.
Project name | Single stage rocket with autonomous recovery guidance system by Parafoil
Club name | Kyutech (Kyushu Institute of Technology) Space Club
YOUR PROJECT
Type of project | Experimental rocket
Type of propellor | Orignal (Pro75-3G)
EXPERIMENT
An experimental project for which the main(s) experiment(s) is (are) not functionning can't be set up.
The secondary experiment is optional. Your project may contain a single or several main experiment(s)
Do not fill this part if your project is a rocket without onboard experiment
Main experiment(s) |  | Experimental rocket with autonomous recovery guidance system by Parafoil
Parameter(s) to measure (mention the units) |  | Flight Direction
For each parameter, precise the expected result |  | Land at target point using onboard navigation, guidance and control system
Secondary experiment(s) (optional) |  | Not decided
Parameter(s) to measure (mention the units)
For each parameter, precise the expected result
Parameter(s) actually sensed (mention the units)
Sensor(s) involved |  | GPS, Digital compass, Differential pressure (pitot+pressure sensor), IMU
Mention here the data conversion formulae |  | GPS and digital compass information acquisition, pitot pressure(total and static) measurement, integration of angular velocities
Data storage medium |  | Onboard recording | FALSE
|  | Ground reception | FALSE
Is there a request for dispensation related to the book of specifications ? |  |  | Select…
If yes, attach the dispensation request |  |  | FALSE
TELEMETRY
Fill this section only if you plan to make use of a transmitter for your project
* This mode is dedicated to the transmission of more than 4 analog signals. The range for each signal is 0 to 5V
** Check this box in case if you plan to make use of a frequency requiring a radio-amateur licence
Main transmitter involved |  | Select…
Radio-amateur Licence** |  |  | FALSE
Attach the autorisation from the radio-amateur (if necessary) |  |  | FALSE |  | FALSE
Precise the type of telemetry |  | Select…
Do you plan to develop your own software tool for telemetry decoding ? |  | Select…
Precise power autonomy
Is there any other source of emission ? |  | Select…
RECOVERY SYSTEM
Precise the type of recovery system you plan to set up |  | Select…
Precise the fall down speed (m/s)
Precise the type of ejection you plan to set up |  | Select…
Precise which system you plan to set up in order trigger and to eject your recovery system ? (several choices allowed) |  | Plug | FALSE | Magnection suction | FALSE
|  | Timer | FALSE | Igniter | FALSE
|  | Servo-Motor | FALSE | Pneumatic jack | FALSE
|  | Other (precise) | FALSE
Precise the autonomy of the system (s)
MECHANICS
This section deals only with rockets. Skip it in case of Balloon.
What part of the rocket is bearing the thrust efforts ? |  |  | Select…
Please attach a drawing at scale of the overall rocket |  |  | FALSE
Please attach a sketch of the thrust plate |  |  | FALSE
STABILITY
Please attach the trajec .par file of the rocket |  |  | FALSE
ONBOARD PROCESSING
Fill this section only if your project includes one or more microcontroler(s)
Any onboard processor or controler ? |  | Select…
Not decided
Navigation Information Acquisition and NGC Calculation to Command Actuators and Telemetry transmission
SAFETY
Please attached the technical files and/or datasheet related to the systems you are using.
*Pyrotechnic system is understood as any other igniter than Davey-Bickford type.
Do you use pyrotechnics* systems onboard ? |  |  | Select…
Do you use pneumatics systems onboard ? |  |  | Select…
Do you use of one or several fumigatory systems onboard ? |  |  | Select…
Is a Risk Analysis available ? |  |  | Select…
If yes, please attach the safety file |  |  | FALSE
COMMENTS
This section is dedicated for technical comments made by CNES and Planete Sciences about your project
Planète Sciences
The drawing at scale of the overall rocket is missing
The sketch of the thrust plate is missing
The trajec .par file of the rocket is missing
CNES

## 4a-Avancement_minif
FEUILLE DE POURCENTAGE
2011-2012
Nom du Projet | [5 empty] | Date de mise à jour
Type de projet |  |  | MINIFUSEE |  |  | Pourcentage atteint | [5 empty] | 0%
|  | Pourcentage de l'expérience secondaire atteint | [9 empty] | 0%
Définition d'expérience |  | 0 |  |  | Général |  |  |  |  | 0
Mécanique |  | 0 |  |  | Définition d'expérience |  |  |  |  | 0
Stabilité |  | 0 |  |  | Expérience |  |  |  |  | 0
Séquenceur |  | 0 |  |  | Télémesure / Stockage |  |  |  |  | 0
Tous les documents dont il est question ici sont des documents internes au projet. Les fiches Planète-Sciences n'en font pas partie
Définition d'expérience | [10 empty] | Total : | 0 | / | 8
Commentaires :
[6 empty] | 0% | 50% | 100%
[6 empty] | NON | Partiel | OUI |  |  | Rappel :
Il existe un document (autre que les fiches Planète-Sciences) … | [8 empty] | Max. | Réel | - Principale : système de récupération
… décrivant le fonctionnement du système de récupération
[6 empty] | Total : |  |  | 8%
Mécanique | [10 empty] | Total : | 0 | / | 33
Commentaires :
Combien de bagues mécaniques comportent le projet :
[6 empty] | 25% | 75% | 100%
[6 empty] | Plan déf° | Réalisée | Intégrée
[9 empty] | Max. | Réel
| Nom bague 1: | [7 empty] | 2%
| Nom bague 2: | [7 empty] | 2%
| Nom bague 3: | [7 empty] | 2%
| Nom bague 4: | [7 empty] | 2%
[6 empty] | Total : |  |  | 8%
[6 empty] | 0% | 75% | 100%
[6 empty] | NON | OUI Partiel | OUI tout |  |  | Rappel :
[9 empty] | Max. | Réel | Il est possible de demander à Planète Sciences un propulseur vide afin de tester la compatibilité propulseur
L'ogive est-elle réalisée ? | [8 empty] | 4%
Les pièces de structure interne sont-elles réalisées ? | [8 empty] | 4%
Le corp de la fusée est il réalisé ? | [8 empty] | 4%
Le parachute de la fusée est il réalisé ? | [8 empty] | 6%
[6 empty] | Total : |  |  | 18%
[6 empty] | 0% | 25% | 100%
[6 empty] | Pas testable | NOK | OK | Max. | Réel | Rappel :
Résultat de la compatibilité propulseur | [8 empty] | 4% |  | Compatibilité rampe = jack, inter, ailerons
Résultat de la compatibilité rampe | [8 empty] | 3%
[6 empty] | Total : |  |  | 7% | 0%
Stabilité | [10 empty] | Total : | 0 | / | 17
Commentaires :
[6 empty] | 0% | 50% | 100%
|  |  | Valeur | Critère |  | Pas calculé | NOK | OK
|  |  | (0 si pas calculé) | [5 empty] | Max. | Réel
Vitesse de sortie de rampe : |  |  | 0 | ≥ 20 m.s-1 |  | x |  |  | 1% | 0%
Finesse : |  |  | 0 | 10 ≤ Cf ≤ 35 |  | x |  |  | 1% | 0%
Portance : |  |  | 0 | 10 ≤ Cn ≤ 40 |  | x |  |  | 1% | 0%
Marge Statique : |  |  | 0 | 2 ≤ Ms ≤ 6 |  | x |  |  | 1% | 0%
Produit Ms x Cn : |  |  | 0 | 40 < MsxCn (< 100) |  | x |  |  | 1% | 0%
[6 empty] | Total : |  |  | 5% | 0%
[6 empty] | 0% | 50% | 100%
[6 empty] | NON | Pb V en sortie | OUI | Max. | Réel
La fusée répond elle aux critères de stabilité
[6 empty] | Total : |  |  | 8%
[6 empty] | 25% | 50% | 100%
[6 empty] | Dimen- sionnés | Réalisés | Fixés | Max. | Réel
Avancement des ailerons …
[6 empty] | Total : |  |  | 4%
Séquenceur | [10 empty] | Total : | 0 | / | 28
Commentaires :
[6 empty] | 0% | 50% | 100%
[6 empty] | Plan | Réalisé | Intégré
Etat d'avancement de/du … | [8 empty] | Max. | Réel | Rappel :
… toutes les pièces mécaniques relatives au système d'ouverture | [8 empty] | 5% |  | les témoins pour vérifier l'état du sytème peuvent tre visuels, sonores…
… sécurité pyrotechnique | [8 empty] | 2%
… témoin de l'état réel du système | [8 empty] | 3%
[6 empty] | Total : |  |  | 10%
[6 empty] | 25% | 50% | 100%
[6 empty] | Proto | Carte soudée | Carte testée | Max. | Réel
La minuterie est au stade …
[6 empty] | Total : |  |  | 8%
[6 empty] | 0% | 50% | 100%
[6 empty] | NON | OK 1 fois | OK 3 fois | Max. | Réel | Rappel :
Test totalement intégré du système de récupération | [10 empty] | Ce test comprend Jack / Accéléro
[6 empty] | Total : |  |  | 10% |  | jusqu'à la sortie du parachute
Général | [10 empty] | Total : | 0 | / | 14
[6 empty] | 0% | 50% | 100%
[6 empty] | NON | Partiel | OUI | Max. | Réel
Le cablage inter-cartes est-il réalisé ? | [8 empty] | 4% |  | Rappel :
La fusée fonctionne-t-elle avec sa source d'energie finale (Piles …) | [8 empty] | 5% |  | Compatibilité rampe = jack, inter, ailerons
Existe-il un document de chronologie avant le vol ? | [8 empty] | 5%
[6 empty] | Total : |  |  | 14%
Définition d'expérience | [10 empty] | Total : | 0 | / | 30 | 100
Commentaires :
[6 empty] | 0% | 50% | 100%
[6 empty] | NON | Partiel | OUI |  |  | Rappel :
Il existe un document (autre que les fiches Planète-Sciences) … | [8 empty] | Max. | Réel
… décrivant l'objectif de l'étude | [8 empty] | 5%
… consignant les expériences | [8 empty] | 5%
[6 empty] | Total : |  |  | 10%
Pour l'étude …
… combien de paramètres physiques sont mesurés à bord :
[6 empty] | 0% | 75% | 100%
[6 empty] | NON | OUI | Avec Justification
| Il existe un doc consignant pour le … | [7 empty] | Max. | Réel | Exemple :
| …paramètre 1: | [9 empty] | - Paramètre = Altitude
|  | Domaine de variation | [8 empty] | - D de Variation : 0m è 750m
|  | Précision attendue | [8 empty] | - Précision : ± 3m
|  | Grandeur effectivement mesurée | [8 empty] | - Mesure : Press° Atmosphérique
|  | Formule de conversion (Mesure > Paramètre) | [8 empty] | - Altitude (m) = 3,14 x P (en Pa)
|  | Evaluation des erreurs de mesures | [8 empty] | - Erreur : ± 1,414Pa soit 4,4m
|  | Méthode d'étalonnage | [8 empty] | - Méthode : 6 pts au manomètre
…paramètre 2:
Domaine de variation
Precisison attendue
|  | Grandeur effectivement mesurée | [8 empty] | Rappel :
|  | Formule de conversion (Mesure > Paramètre) | [8 empty] | un paramètre peut être mesuré en plusieurs point de la fusée càd 1 paramètre = plusieurs capteurs
Evaluation des erreurs de mesures
Méthode d'étalonnage
[6 empty] | Total : |  |  | 20%
Expérience | [10 empty] | Total : | 0 | / | 30
Commentaires :
Combien de carte élec comporte le projet (hors séquenceur) :
[6 empty] | 50% | 75% | 100% |  |  | Rappel :
[6 empty] | Carte Soudée | Carte Testée | Doc. Minimale |  |  | "Doc. Minimale" = impression de
[9 empty] | Max. | Réel | - Schéma électrique
| Carte élec 1: | [9 empty] | - Routage
| Carte élec 2: | [9 empty] | - Plan d'implantat° des compo
| Carte élec 3: | [9 empty] | dans la version de la carte actuelle
Carte élec 4:
Carte élec 5:
Carte élec 6:
[6 empty] | Total : |  |  | 13%
[6 empty] | 0% | 75% | 100% |  |  | Rappel :
[6 empty] | NON | Partiel | OUI |  |  | "Doc. Minimale" = impression de
Il existe un … | [8 empty] | Max. | Réel | - Schéma électrique
… plan de cablage général de toutes les cartes | [8 empty] | 4% |  | - Routage
… plan précisant l'intégration électronique / mécanique | [8 empty] | 3% |  | - Plan d'implantat° des compo
[6 empty] | Total : |  |  | 7% |  | dans la version de la carte actuelle
Etalonnage des capteurs …
Combien de capteurs comporte le projet :
[6 empty] | 0% | 75% | 100% |  |  | Rappel :
[6 empty] | Non Etalonné | Etalonné ≤3 pts | Etalonné ≥3 pts
[9 empty] | Max. | Réel | Pour étaloner les capteurs, la mesure doit se faire à l'entrée de l'émetteur
Capteur 1:
Capteur 2:
Capteur 3:
Capteur 4:
Capteur 5:
[6 empty] | Total : |  |  | 10%
Télémesure / Stockage | [10 empty] | Total : | 0 | / | 40
Commentaires :
[6 empty] | NON | OUI
Le projet comporte …
… une télémesure
… une sauvegarde des données installée dans la fusée
[6 empty] | 0% | 25% | 100%
Pour la télémesure … | [5 empty] | Démo impossible | Test - NOK | Test - OK | Max. | Réel
Démonstration de [codage / émission / réception / décodage]
[6 empty] | Total : |  |  | 0%
[6 empty] | 0% | 25% | 100%
Pour le stockage … | [5 empty] | Démo impossible | Test - NOK | Test - OK | Max. | Réel
Démonstration de "codage / stockage / lecture / décodage"
[6 empty] | Total : |  |  | 0%

## 4a-Progress_mini-rocket
PERCENTAGE FORM
2011-2012
Project Name | [5 empty] | Update date
Project Type |  |  | MINIFUSEE |  |  | Percentage reached | [5 empty] | 0%
|  | Secondary experiment percentage reached | [9 empty] | 0%
Experiment definition |  | 0 |  |  | Global |  |  |  |  | 0
Mecahnical parts |  | 0 |  |  | Experiment definition |  |  |  |  | 0
Stability |  | 0 |  |  | Experiment |  |  |  |  | 0
Sequencer |  | 0 |  |  | Telemetry/storage |  |  |  |  | 0
All the documents mentioned below are belonging to the project and are not referring to the Planète Sciences forms.
Experiment definition | [10 empty] | Total : | 0 | / | 8
Comments:
[6 empty] | 0% | 50% | 100%
[6 empty] | NO | Partly | YES |  |  | Reminder:
Availability of a document (other than the Planète Scicence forms)… | [8 empty] | Max. | Real | - Main: recovery system
… describing how the recovery system works
[6 empty] | Total : |  |  | 8%
Mechanical parts | [10 empty] | Total : | 0 | / | 33
Comments:
How many mechanical rings are included in your project ?
[6 empty] | 25% | 75% | 100%
[6 empty] | Def. Sketch | Done | Integrated
[9 empty] | Max. | Real
| #1 ring name | [7 empty] | 2%
| #2 ring name | [7 empty] | 2%
| #3 ring name | [7 empty] | 2%
| #4 ring name | [7 empty] | 2%
[6 empty] | Total : |  |  | 8%
[6 empty] | 0% | 75% | 100%
[6 empty] | YES | Partly | YES all |  |  | Reminder:
[9 empty] | Max. | Real | You may request Planète Sciences to provide you with an empty propeller for the purpose of mecahnical tests
Is the nose cone manufactured ? | [8 empty] | 4%
Are the parts of the internal structure manufactured ? | [8 empty] | 4%
Is the body ofthe rocket manufactured ? | [8 empty] | 4%
Is the parachute manufactured ? | [8 empty] | 6%
[6 empty] | Total : |  |  | 18%
[6 empty] | 0% | 25% | 100%
[6 empty] | Cannot be tested | Not OK | OK | Max. | Real | Reminder:
Propeller compatibility test result | [8 empty] | 4% |  | Launching pad compatibility : plug, switch, fins
Launching pad compatibility test result | [8 empty] | 3%
[6 empty] | Total : |  |  | 7% | 0%
Stability | [10 empty] | Total : | 0 | / | 17
Comments:
[6 empty] | 0% | 50% | 100%
|  |  | Value | Criterion |  | Not calculated | Not OK | OK
|  |  | (0 if not calculated) | [5 empty] | Max. | Real
Out pad speed |  |  | 0 | ≥ 20 m.s-1 |  | x |  |  | 1% | 0%
Lift to drag ratio (Cf) |  |  | 0 | 10 ≤ Cf ≤ 35 |  | x |  |  | 1% | 0%
Lift (Cn) |  |  | 0 | 10 ≤ Cn ≤ 40 |  | x |  |  | 1% | 0%
Static margin (MS) |  |  | 0 | 2 ≤ Ms ≤ 6 |  | x |  |  | 1% | 0%
Ms x Cn product |  |  | 0 | 40 < MsxCn (< 100) |  | x |  |  | 1% | 0%
[6 empty] | Total : |  |  | 5% | 0%
[6 empty] | 0% | 50% | 100%
[6 empty] | NO | Out speed problem | YES | Max. | Real
Is the rocket compatible with the stability criterions ?
[6 empty] | Total : |  |  | 8%
[6 empty] | 25% | 50% | 100%
[6 empty] | Dimensionned | Done | Attached | Max. | Real
Progress on the fins…
[6 empty] | Total : |  |  | 4%
Sequencer | [10 empty] | Total : | 0 | / | 28
Comments:
[6 empty] | 0% | 50% | 100%
[6 empty] | Sketch | Done | Integrated
Progress status of… | [8 empty] | Max. | Real | Reminder:
… all the mecanical parts related to the recovery system | [8 empty] | 5% |  | Indicators aim at describing the system status can be visual, audible…
… pyrotechnic safety | [8 empty] | 2%
… actual system status indicator | [8 empty] | 3%
[6 empty] | Total : |  |  | 10%
[6 empty] | 25% | 50% | 100%
[6 empty] | Prototype | PCB soldered | Board tested | Max. | Real
Timer system has reached the status of…
[6 empty] | Total : |  |  | 8%
[6 empty] | 0% | 50% | 100%
[6 empty] | NO | OK 1 time | OK 3 times | Max. | Real | Reminder:
Complete test of the integrated recovery system | [10 empty] | This test starts from the trigger,accelerometer…ends with the parachute ejection.
[6 empty] | Total : |  |  | 10%
Global | [10 empty] | Total : | 0 | / | 14
[6 empty] | 0% | 50% | 100%
[6 empty] | NO | Partly | YES | Max. | Real
Is inter boards wiring done ? | [8 empty] | 4% |  | Reminder:
Is the rocket powered with its final source of energy (batteries…) | [8 empty] | 5% |  | Launching pad compatibility : plug, switch, fins
Is the pre-flight chronological tasklist available ? | [8 empty] | 5%
[6 empty] | Total : |  |  | 14%
Experiment definition | [10 empty] | Total : | 0 | / | 30 | 100
Comments:
[6 empty] | 0% | 50% | 100%
[6 empty] | NO | Partly | YES |  |  | Reminder:
Availability of a document (other than the Planète Scicence forms)… | [8 empty] | Max. | Real
… describing the purpose and aim of the study | [8 empty] | 5%
… listing the experiments | [8 empty] | 5%
[6 empty] | Total : |  |  | 10%
For the study…..
… how many parameters are measured onboard the rocket ?
[6 empty] | 0% | 75% | 100%
[6 empty] | NO | YES | With justification
| Availability of a description document for the… | [7 empty] | Max. | Real | Example :
| …parametre #1: | [9 empty] | - Parametre = Altitude
|  | Variation range | [8 empty] | - Variation Range : 0m è 750m
|  | Expected precision | [8 empty] | - Precision : ± 3m
|  | Actual measure | [8 empty] | - Measure : Atmosphere pressure
|  | Conversion formula (Measure > Parametre) | [8 empty] | - Altitude (m) = 3,14 x P (in Pa)
|  | Measurement errors evaluation | [8 empty] | - Error : ± 1,414Pa, ie 4,4m
|  | Calibration methodology | [8 empty] | - Methodology : 6 pts with manometre
…parametre #2:
Variation range
Expected precision
|  | Actual measure | [8 empty] | Reminder:
|  | Conversion formula (Measure > Parametre) | [8 empty] | One parametre may be measured in severalpoints in the rocket that is to say 1 parameter = several sensors
Measurement errors evaluation
Calibration methodology
[6 empty] | Total : |  |  | 20%
Experiment | [10 empty] | Total : | 0 | / | 30
Comments:
How many electronic boards onboard (except sequencer) ?
[6 empty] | 50% | 75% | 100% |  |  | Reminder:
[6 empty] | Soldered | Tested | Minimum Doc. |  |  | "Minimum Doc" = printout of
[9 empty] | Max. | Real | - Electronics schematics
| Elec. Board #1: | [9 empty] | - Routing
| Elec. Board #2: | [9 empty] | - Placement of the parts on PCB
| Elec. Board #3: | [9 empty] | in the current available version
Elec. Board #4:
Elec. Board #5:
Elec. Board #6:
[6 empty] | Total : |  |  | 13%
[6 empty] | 0% | 75% | 100% |  |  | Reminder:
[6 empty] | NO | Partly | YES |  |  | "Minimum Doc" = printout of
Availability of… | [8 empty] | Max. | Real | - Electronics schematics
… a global wiring map of all the boards | [8 empty] | 4% |  | - Routing
… a drawing describing electromechanics integration | [8 empty] | 3% |  | - Placement of the parts on PCB
[6 empty] | Total : |  |  | 7% |  | in the current available version
Sensors calibration…
How many sensors onboard ?
[6 empty] | 0% | 75% | 100% |  |  | Reminder:
[6 empty] | Not calibrated | Calibrated with ≤3 points | Calibrated with ≥3 pts
[9 empty] | Max. | Real | Sensors calibration must be performed from the input of the transmitter
Sensor #1:
Sensor #2:
Sensor #3:
Sensor #4:
Sensor #5:
[6 empty] | Total : |  |  | 10%
Telemetry / Storage | [10 empty] | Total : | 0 | / | 40
Comments:
[6 empty] | NO | YES
The project includes…
… a telemetry system
… a data storage device inside the rocket
[6 empty] | 0% | 25% | 100%
For telemetry… | [5 empty] | Not demonstrable | Tested - Not OK | Tested - OK | Max. | Real
[Coding/transmission/reception/decoding] has been demonstrated
[6 empty] | Total : |  |  | 0%
[6 empty] | 0% | 25% | 100%
For storage… | [5 empty] | Not demonstrable | Tested - Not OK | Tested - OK | Max. | Real
[Coding/transmission/reception/decoding] has been demonstrated
[6 empty] | Total : |  |  | 0%

## 4b-Avancement_fusex
FEUILLE DE POURCENTAGE
2011-2012
Nom du Projet | [5 empty] | Date de mise à jour
Type de projet |  |  | FUSEX |  |  | Pourcentage atteint | [5 empty] | 0%
Définition d'expérience |  | 0 |  |  | Stabilité |  |  |  | 0
Mécanique |  | 0 |  |  | Séquenceur |  |  |  | 0
Expérience |  | 0 |  |  | Informatique |  |  |  | 0
Télémesure / Stockage |  | 0 |  |  | Général |  |  |  | 0
Tous les documents dont il est question ici sont des documents internes au projet. Les fiches Planète-Sciences n'en font pas partie
Pour remplir cette fiche, mettre un 'x' dans les cases (ou un chiffre quand c'est demandé)
Définition d'expérience | [10 empty] | Total | 0 | / | 10
Commentaires :
[6 empty] | 0% | 50% | 100%
[6 empty] | NON | Partiel | OUI |  |  | Rappel :
Il existe un document (autre que les fiches Planète-Sciences) … | [8 empty] | Max. | Réel | - Principale : mon projet n'a pas
… décrivant le but de/des expériences | [8 empty] | 2% |  | lieu d'être sans.
… consignant les expériences principales et secondaires | [8 empty] | 2% |  | - Secondaire : non vital au projet
[6 empty] | Total : |  |  | 4%
Pour les expériences principales …
… combien de paramètres physiques sont mesurés à bord :
[6 empty] | 0% | 75% | 100%
[6 empty] | NON | OUI | Avec Justification
| Il existe un doc consignant pour le … | [7 empty] | Max. | Réel | Exemple :
| …paramètre 1: | [9 empty] | - Paramètre = Altitude
|  | Domaine de variation | [8 empty] | - D de Variation : 0m è 750m
|  | Précision attendue | [8 empty] | - Précision : ± 3m
|  | Grandeur effectivement mesurée | [8 empty] | - Mesure : Press° Atmosphérique
|  | Formule de conversion (Mesure > Paramètre) | [8 empty] | - Altitude (m) = 3,14 x P (en Pa)
|  | Evaluation des erreurs de mesures | [8 empty] | - Erreur : ± 1,414Pa soit 4,4m
|  | Méthode d'étalonnage | [8 empty] | - Méthode : 6 pts au manomètre
…paramètre 2:
Domaine de variation
Precisison attendue
|  | Grandeur effectivement mesurée | [8 empty] | Rappel :
|  | Formule de conversion (Mesure > Paramètre) | [8 empty] | - un paramètre peut être mesuré
|  | Evaluation des erreurs de mesures | [8 empty] | en plusieurs point de la Fusex
|  | Méthode d'étalonnage | [8 empty] | càd 1 paramètre = pls capteurs
…paramètre 3:
Domaine de variation
Precisison attendue
Grandeur effectivement mesurée
Formule de conversion (Mesure > Paramètre)
Evaluation des erreurs de mesures
Méthode d'étalonnage
…paramètre 4:
Domaine de variation
Precisison attendue
Grandeur effectivement mesurée
Formule de conversion (Mesure > Paramètre)
Evaluation des erreurs de mesures
Méthode d'étalonnage
…paramètre 5:
Domaine de variation
Precisison attendue
Grandeur effectivement mesurée
Formule de conversion (Mesure > Paramètre)
Evaluation des erreurs de mesures
Méthode d'étalonnage
…paramètre 6:
Domaine de variation
Precisison attendue
Grandeur effectivement mesurée
Formule de conversion (Mesure > Paramètre)
Evaluation des erreurs de mesures
Méthode d'étalonnage
[6 empty] | Total : |  |  | 6%
Mécanique | [10 empty] | Total : | 0 | / | 15
Commentaires :
Combien de bagues mécaniques comportent le projet :
[6 empty] | 0% | 50% | 100%
[6 empty] | Non fait | Réalisée | Intégrée
[9 empty] | Max. | Réel
Nom bague 1:
Nom bague 2:
Nom bague 3:
Nom bague 4:
Nom bague 5:
Nom bague 6:
[6 empty] | Total : |  |  | 4%
[6 empty] | 0% | 75% | 100%
[6 empty] | NON | OUI Partiel | OUI tout |  |  | Rappel :
[9 empty] | Max. | Réel | - Principale : mon projet n'a pas
L'ogive est-elle réalisée ? | [8 empty] | 4% |  | lieu d'être sans.
Les pièces de structure interne sont-elles réalisées ? | [8 empty] | 2% |  | - Secondaire : non vital au projet
Les peaux sont-elles réalisées ? | [8 empty] | 2%
[6 empty] | Total : |  |  | 8%
[6 empty] | 0% | 25% | 100%
[6 empty] | Pas testable | NOK | OK | Max. | Réel
Résultat de la compatibilité propulseur
[6 empty] | Total : |  |  | 3%
Expérience | [10 empty] | Total : | 0 | / | 16
Commentaires :
Combien de carte élec comporte le projet (hors séquenceur) :
[6 empty] | 0% | 50% | 100% |  |  | Rappel :
[6 empty] | Non fait | Carte Réalisée | Carte Testée |  |  | "Doc. Minimale" = impression de
[9 empty] | Max. | Réel | - Schéma électrique
| Carte élec 1: | [9 empty] | - Routage
| Carte élec 2: | [9 empty] | - Plan d'implantat° des compo
| Carte élec 3: | [9 empty] | dans la version de la carte actuelle
Carte élec 4:
Carte élec 5:
Carte élec 6:
[6 empty] | Total : |  |  | 6%
[6 empty] | 0% | 75% | 100%
[6 empty] | NON | Partiel | OUI
Il existe un … | [8 empty] | Max. | Réel
… plan de cablage général de toutes les cartes | [8 empty] | 3%
… plan précisant l'intégration électronique / mécanique | [8 empty] | 1%
[6 empty] | Total : |  |  | 4%
Etalonnage des capteurs …
Combien de capteurs comporte le projet :
[6 empty] | 0% | 75% | 100% |  |  | Rappel :
[6 empty] | Non Etalonné | Etalonné ≤3 pts | Etalonné ≥3 pts |  |  | "Doc. Minimale" = impression de
[9 empty] | Max. | Réel | - Schéma électrique
| Capteur 1: | [9 empty] | - Routage
| Capteur 2: | [9 empty] | - Plan d'implantat° des compo
| Capteur 3: | [9 empty] | dans la version de la carte actuelle
Capteur 4:
Capteur 5:
Capteur 6:
[6 empty] | Total : |  |  | 6%
Télémesure / Stockage | [10 empty] | Total : | 0 | / | 12
Commentaires :
[6 empty] | NON | OUI
Le projet comporte …
… une télémesure
… une sauvegarde des données installée dans la fusée
[6 empty] | 0% | 25% | 100%
Pour la télémesure … | [5 empty] | Démo impossible | Test - NOK | Test - OK | Max. | Réel
Démonstration de [codage / émission / réception / décodage]
[6 empty] | Total : |  |  | 6~12%
[6 empty] | 0% | 25% | 100%
Pour le stockage … | [5 empty] | Démo impossible | Test - NOK | Test - OK | Max. | Réel
Démonstration de [codage / émission / réception / décodage]
[6 empty] | Total : |  |  | 6~12%
Stabilité | [10 empty] | Total : | 0 | / | 8
Commentaires :
[6 empty] | 0% | 50% | 100%
|  |  | Valeur | Critère |  | Pas calculé | NOK | OK
|  |  | (0 si pas calculé) | [5 empty] | Max. | Réel
Vitesse de sortie de rampe : |  |  | 0 | ≥ 20 m.s-1 |  | x |  |  | 1% | 0%
Finesse : |  |  | 0 | 10 ≤ Cf ≤ 35 |  | x |  |  | 1% | 0%
Portance : |  |  | 0 | 10 ≤ Cn ≤ 40 |  | x |  |  | 1% | 0%
Marge Statique : |  |  | 0 | 2 ≤ Ms ≤ 6 |  | x |  |  | 1% | 0%
Produit Ms x Cn : |  |  | 0 | 40 < MsxCn (< 100) |  | x |  |  | 1% | 0%
[6 empty] | Total : |  |  | 5% | 0%
[6 empty] | 0% | 50% | 100%
[6 empty] | Non fait | Réalisés | Fixés | Max. | Réel
Avancement des ailerons …
[6 empty] | Total : |  |  | 3%
Séquenceur | [10 empty] | Total : | 0 | / | 20
Commentaires :
[6 empty] | 0% | 50% | 100%
[6 empty] | Plan | Réalisé | Intégré
Etat d'avancement de/du … | [8 empty] | Max. | Réel | Rappel :
… toutes les pièces mécaniques relatives au système d'ouverture | [8 empty] | 3% |  | Intégrat° parachute = compatibilité
… parachute | [8 empty] | 2% |  | avec la case parachute.
[6 empty] | Total : |  |  | 5%
[6 empty] | 0% | 50% | 100%
[6 empty] | Non fait | Carte soudée | Carte testée | Max. | Réel
La minuterie est au stade …
[6 empty] | Total : |  |  | 5%
[6 empty] | 0% | 50% | 100%
[6 empty] | NOK | OK 1 fois | OK 3 fois | Max. | Réel | Rappel :
Test totalement intégré du système de récupération | [10 empty] | Ce test comprend Jack / Accéléro
[6 empty] | Total : |  |  | 10% |  | jusqu'à la sortie du parachute
Informatique | [10 empty] | Total : | 0 | / | 6
Combien de microcontrolleur comporte la fusex ?
[6 empty] | 0% | 75% | 100%
[6 empty] | Non fait | Marche sur carte finale | Marche dans la fusex
| Etat d'avancement du programme pour … | [7 empty] | Max. | Réel
Nom microcontrolleur 1 :
Nom microcontrolleur 2 :
Nom microcontrolleur 3 :
Nom microcontrolleur 4 :
Nom microcontrolleur 5 :
Nom microcontrolleur 6 :
[6 empty] | Total : |  |  | 6%
Général | [10 empty] | Total : | 0 | / | 13
[6 empty] | 0% | 50% | 100%
[6 empty] | NON | Partiel | OUI | Max. | Réel
Le cablage inter-cartes est-il réalisé ? | [8 empty] | 4% |  | Rappel :
La fusée fonctionne-t-elle avec sa source d'energie finale (Piles …) | [8 empty] | 5% |  | Compatibilité rampe = jack, inter,
La compatibilité rampe est-elle bonne ? | [8 empty] | 2% |  | Ailerons ….
Existe-il un document de chronologie avant le vol ? | [8 empty] | 2%
[6 empty] | Total : |  |  | 13%

## 4b-Progress_fusex
PERCENTAGE FORM
2011-2012
Project Name |  |  | Single stage rocket with autonomous recovery guidance system by Parafoil |  |  |  | Update date | [5 empty] | Jan. 27, 2011
Project Type |  |  | FUSEX |  |  |  | Percentage reached | [5 empty] | 4%
Experiment definition |  | 4 |  |  |  | Stability |  |  |  | 0
Mechanics |  | 0 |  |  |  | Sequencer |  |  |  | 0
Experiment |  | 0 |  |  |  | Onboard process |  |  |  | 0
Telemetry/storage |  | 0 |  |  |  | Global |  |  |  | 0
All the documents mentioned below are belonging to the project and are not referring to the Planète Sciences forms.
Experiment definition | [11 empty] | Total | 4 | / | 10
Comments:
[7 empty] | 0% | 50% | 100%
[7 empty] | NO | Parlty | YES |  |  | Reminder:
Availability of a document (other than the Planète Scicence forms)… | [9 empty] | Max. | Real | - Principale : mon projet n'a pas
… describing the purpose and aim of the study | [8 empty] | x | 2% | 2% | lieu d'être sans.
… listing the experiments | [8 empty] | x | 2% | 2% | - Secondaire : non vital au projet
[7 empty] | Total : |  |  | 4% | 4%
For the main experiments…
… how many parameters are measured onboard the rocket ? | [6 empty] | 5
[7 empty] | 0% | 75% | 100%
[7 empty] | NO | YES | With justification
| Availability of a description document for the… | [8 empty] | Max. | Real | Exemple :
| …parameter #1: |  | Pressure (pitot and pressure sensor) | [8 empty] | - Parametre = Altitude
|  | Variation range |  |  |  |  | x |  |  | 0.2% | 0% | - Variation Range : 0m è 750m
|  | Expected precision |  |  |  |  | x |  |  | 0.2% | 0% | - Precision : ± 3m
|  | Actual measure |  |  |  |  | x |  |  | 0.2% | 0% | - Measure : Atmosphere pressure
|  | Conversion formula (Measure > Parametre) |  |  |  |  | x |  |  | 0.2% | 0% | - Altitude (m) = 3,14 x P (in Pa)
|  | Measurement errors evaluation |  |  |  |  | x |  |  | 0.2% | 0% | - Error : ± 1,414Pa, ie 4,4m
|  | Calibration methodology |  |  |  |  | x |  |  | 0.2% | 0% | - Methodology : 6 pts with manometre
| …parameter #2: |  | Location (GPS)
|  | Variation range |  |  |  |  | x |  |  | 0.2% | 0%
|  | Expected precision |  |  |  |  | x |  |  | 0.2% | 0%
|  | Actual measure |  |  |  |  | x |  |  | 0.2% | 0% | Reminder:
|  | Conversion formula (Measure > Parametre) |  |  |  |  | x |  |  | 0.2% | 0% | One parametre may be measured in severalpoints in the rocket that is to say 1 parameter = several sensors
|  | Measurement errors evaluation |  |  |  |  | x |  |  | 0.2% | 0%
|  | Calibration methodology |  |  |  |  | x |  |  | 0.2% | 0%
| …parameter #3: |  | Flight direction (digital compass)
|  | Variation range |  |  |  |  | x |  |  | 0.2% | 0%
|  | Expected precision |  |  |  |  | x |  |  | 0.2% | 0%
|  | Actual measure |  |  |  |  | x |  |  | 0.2% | 0%
|  | Conversion formula (Measure > Parametre) |  |  |  |  | x |  |  | 0.2% | 0%
|  | Measurement errors evaluation |  |  |  |  | x |  |  | 0.2% | 0%
|  | Calibration methodology |  |  |  |  | x |  |  | 0.2% | 0%
| …parameter #4: |  | Attitude (IMU)
|  | Variation range |  |  |  |  | x |  |  | 0.2% | 0%
|  | Expected precision |  |  |  |  | x |  |  | 0.2% | 0%
|  | Actual measure |  |  |  |  | x |  |  | 0.2% | 0%
|  | Conversion formula (Measure > Parametre) |  |  |  |  | x |  |  | 0.2% | 0%
|  | Measurement errors evaluation |  |  |  |  | x |  |  | 0.2% | 0%
|  | Calibration methodology |  |  |  |  | x |  |  | 0.2% | 0%
| …parameter #5: |  | Altitude (altimeter)
|  | Variation range |  |  |  |  | x |  |  | 0.2% | 0%
|  | Expected precision |  |  |  |  | x |  |  | 0.2% | 0%
|  | Actual measure |  |  |  |  | x |  |  | 0.2% | 0%
|  | Conversion formula (Measure > Parametre) |  |  |  |  | x |  |  | 0.2% | 0%
|  | Measurement errors evaluation |  |  |  |  | x |  |  | 0.2% | 0%
|  | Calibration methodology |  |  |  |  | x |  |  | 0.2% | 0%
…parameter #6:
Variation range
Expected precision
Actual measure
Conversion formula (Measure > Parametre)
Measurement errors evaluation
Calibration methodology
[7 empty] | Total : |  |  | 6% | 0%
Mechanical parts | [11 empty] | Total : | 0 | / | 15
Comments:
How many mechanical rings are included in your project ?
[7 empty] | 0% | 50% | 100%
[7 empty] | Def. Sketch | Done | Integrated
[10 empty] | Max. | Real
| #1 ring name |  | Not decided |  |  |  | x
| #2 ring name | [5 empty] | x
| #3 ring name | [5 empty] | x
| #4 ring name | [5 empty] | x
| #5 ring name | [5 empty] | x
| #6 ring name | [5 empty] | x
[7 empty] | Total : |  |  | 4%
[7 empty] | 0% | 75% | 100%
[7 empty] | NON | OUI Partiel | OUI tout |  |  | Reminder:
[10 empty] | Max. | Real | - Main : a project means nothing without it.
Is the nose cone manufactured ? | [6 empty] | x |  |  | 4% | 0%
Are the parts of the internal structure manufactured ? | [6 empty] | x |  |  | 2% | 0% | - Secondary : will not lead to the project cancellation if not present
Are the skins manufactured ? | [6 empty] | x |  |  | 2% | 0%
[7 empty] | Total : |  |  | 8% | 0%
[7 empty] | 0% | 25% | 100%
[7 empty] | Cannot be tested | Not OK | OK | Max. | Real
Propeller compatibility test result | [6 empty] | x
[7 empty] | Total : |  |  | 3% | 0%
Experiment | [11 empty] | Total : | 0 | / | 16
Comments:
How many electronic boards onboard (except sequencer) ?
[7 empty] | 0% | 50% | 100% |  |  | Reminder:
[7 empty] | Not done | Board done | Board tested |  |  | "Minimum Doc" = printout of
[10 empty] | Max. | Real | - Electronics schematics
| Elec. Board #1: |  | Not decided |  |  |  | x |  |  |  |  | - Routing
| Elec. Board #2: | [5 empty] | x |  |  |  |  | - Placement of the parts on PCB
| Elec. Board #3: | [5 empty] | x |  |  |  |  | in the current available version
| Elec. Board #4: | [5 empty] | x
| Elec. Board #5: | [5 empty] | x
| Elec. Board #6: | [5 empty] | x
[7 empty] | Total : |  |  | 6%
[7 empty] | 0% | 75% | 100%
[7 empty] | NO | Partly | YES
Availability of… | [9 empty] | Max. | Real
… a global wiring map of all the boards | [6 empty] | x |  |  | 3% | 0%
… a drawing describing electromechanics integration | [6 empty] | x |  |  | 1% | 0%
[7 empty] | Total : |  |  | 4% | 0%
Sensors calibration…
How many sensors onboard ? | [6 empty] | 5
[7 empty] | 0% | 75% | 100% |  |  | Reminder:
[7 empty] | Not calibrated | Calibrated with ≤3 points | Calibrated with ≥3 pts |  |  | "Minimum Doc" = printout of
[10 empty] | Max. | Real | - Electronics schematics
| Sensor #1: |  | Pressure sensor |  |  |  | x |  |  | 1.2% | 0% | - Routing
| Sensor #2: |  | GPS |  |  |  | x |  |  | 1.2% | 0% | - Placement of the parts on PCB
| Sensor #3: |  | Digital compass |  |  |  | x |  |  | 1.2% | 0% | in the current available version
| Sensor #4: |  | IMU |  |  |  | x |  |  | 1.2% | 0%
| Sensor #5: |  | Altimeter |  |  |  | x |  |  | 1.2% | 0%
Sensor #6:
[7 empty] | Total : |  |  | 6% | 0%
Telemetry / Storage | [11 empty] | Total : | 0 | / | 12
Comments:
[7 empty] | NO | YES
The project includes…
… a telemetry system | [7 empty] | x
… a data storage device inside the rocket | [7 empty] | x
[7 empty] | 0% | 25% | 100%
For telemetry… | [6 empty] | Not demonstrable | Tested - Not OK | Tested - OK | Max. | Real
[Coding/transmission/reception/decoding] has been demonstrated | [6 empty] | x
[7 empty] | Total : |  |  | 6% | 0%
[7 empty] | 0% | 25% | 100%
Pour le stockage … | [6 empty] | Not demonstrable | Tested - Not OK | Tested - OK | Max. | Real
Démonstration de [codage / émission / réception / décodage] | [6 empty] | x
[7 empty] | Total : |  |  | 6% | 0%
Stability | [11 empty] | Total : | 0 | / | 8
Comments:
[7 empty] | 0% | 50% | 100%
|  |  | Value |  | Criterion |  | Not calculated | Not OK | OK
|  |  | (0 if not calculated) | [6 empty] | Max. | Real
Out pad speed |  |  | 0 |  | ≥ 20 m.s-1 |  | x |  |  | 1% | 0%
Lift to drag ratio (Cf) |  |  | 0 |  | 10 ≤ Cf ≤ 35 |  | x |  |  | 1% | 0%
Lift (Cn) |  |  | 0 |  | 10 ≤ Cn ≤ 40 |  | x |  |  | 1% | 0%
Static margin (MS) |  |  | 0 |  | 2 ≤ Ms ≤ 6 |  | x |  |  | 1% | 0%
Ms x Cn product |  |  | 0 |  | 40 < MsxCn (< 100) |  | x |  |  | 1% | 0%
[7 empty] | Total : |  |  | 5% | 0%
[7 empty] | 0% | 50% | 100%
[7 empty] | Not done | Done | Attached | Max. | Real
Progress on the fins… | [6 empty] | x
[7 empty] | Total : |  |  | 3% | 0%
Sequencer | [11 empty] | Total : | 0 | / | 20
Comments:
[7 empty] | 0% | 50% | 100%
[7 empty] | Sketch | Done | Integrated
Progress status of… | [9 empty] | Max. | Real | Reminder:
… all the mecanical parts related to the recovery system | [6 empty] | x |  |  | 3% | 0% | Parachute integration = compatibility with the parachute room
… parachute | [6 empty] | x |  |  | 2% | 0%
[7 empty] | Total : |  |  | 5% | 0%
[7 empty] | 0% | 50% | 100%
[7 empty] | Not done | PCB soldered | Board tested | Max. | Real
Timer system has reached the status of… | [6 empty] | x
[7 empty] | Total : |  |  | 5% | 0%
[7 empty] | 0% | 50% | 100%
[7 empty] | NO | OK 1 time | OK 3 times | Max. | Real | Reminder:
Complete test of the integrated recovery system | [6 empty] | x |  |  |  |  | This test starts from the trigger,accelerometer…ends with the parachute ejection.
[7 empty] | Total : |  |  | 10% | 0%
Onboard processing | [11 empty] | Total : | 0 | / | 6
How many processors onboard ?
[7 empty] | 0% | 75% | 100%
[7 empty] | Notedone | Runs on final board | Runs in the Fusex
| Code progress for… | [8 empty] | Max. | Real
| Microcontroler #1 : |  |  | Not decided |  |  | x
| Microcontroler #2 : | [5 empty] | x
| Microcontroler #3 : | [5 empty] | x
| Microcontroler #4 : | [5 empty] | x
| Microcontroler #5 : | [5 empty] | x
| Microcontroler #6 : | [5 empty] | x
[7 empty] | Total : |  |  | 6%
Global | [11 empty] | Total : | 0 | / | 13
[7 empty] | 0% | 50% | 100%
[7 empty] | NO | Partly | YES | Max. | Real
Is inter boards wiring done ? | [6 empty] | x |  |  | 4% | 0% | Reminder:
Is the rocket powered with its final source of energy (batteries…) | [6 empty] | x |  |  | 5% | 0% | Launching pad compatibility : plug, switch, fins
Is the rocket compatible with the stability criterions ? | [6 empty] | x |  |  | 2% | 0%
Is the pre-flight chronological tasklist available ? | [6 empty] | x |  |  | 2% | 0%
[7 empty] | Total : |  |  | 13% | 0%

## 5-Dérogation
2011-2012
Fiche de demande de dérogation
A retourner avant le 17 mars 2012
UNE FICHE PAR PROJET
Cette fiche de demande de dérogation est obligatoire pour tout projet faisant l'objet d'une demande de dérogation à une règle du Cahier des Charges.
A partir des informations contenues dans cette fiche, le CNES et Planète Sciences analyseront et accepteront ou non la demande;
Nom du projet
Nom du club
VOTRE PROJET
Type de projet | Sélectionner …
DEMANDE DE DEROGATION
Indiquez la règle que vous souhaitez déroger
Pourquoi ?
Avez vous réalisé une analyse de risques ? |  | OUI | FALSE
Vous devez analyser les conséquences sur la sécurité en cas de défaillance de votre système et juger de la criticité
Quel est l'impact pour votre projet si la demande est refusé |  | Sélectionner …
Précisez
DEMANDE DE DEROGATION
Indiquez la règle que vous souhaitez déroger
Pourquoi ?
Avez vous réalisé une analyse de risques ? |  | OUI | FALSE
Vous devez analyser les conséquences sur la sécurité en cas de défaillance de votre système et juger de la criticité
Quel est l'impact pour votre projet si la demande est refusé |  | Sélectionner …
Précisez
COMMENTAIRES
Cette partie est réservée à Planète Sciences pour y faire des remarques concernant votre projet
La demande de dérogation au Cahier des Charges est elle aceptée ? |  |  |  | Sélectionner …
Ce projet est-il spécial ? |  |  |  | Sélectionner …
Un dossier de sécurité est-il demandé ? |  |  |  | Sélectionner …

## 5-Dispensation
2011-2012
Dispensation request file
To be returned before March17th 2012
ONE FORM PER PROJECT
This dispensation request form is mandatory for any project which requires a dispensation related to the Book of Specifications.
From the information provided in this form, CNES and Planète Sciences will analyse and accept or not the request.
Project name | Single stage rocket with autonomous recovery guidance system by Parafoil
Club name | Kyutech (Kyushu Institute of Technology) Space Club
YOUR PROJECT
Type of project | Select…
DISPENSATION REQUEST
For which rule do you request for dispensation ?
Why ?
Did you prepare a risk analysis ? |  | YES | FALSE
You must analyse the consequences on safety in case of a system failure, and evaluate its criticity level.
What is the consequence for your project in case if the dispensation is not granted ? |  | Select…
Precise
DISPENSATION REQUEST
For which rule do you request for dispensation ?
Why ?
Did you prepare a risk analysis ? |  | YES | FALSE
You must analyse the consequences on safety in case of a system failure, and evaluate its criticity level.
What is the consequence for your project in case if the dispensation is not granted ? |  | Select…
Precise
COMMENTS
This section is dedicated for comments made by Planete Sciences about your project
Is the request for dispensation related to the book of specifications granted ? |  |  |  | Select…
Is this a special project ? |  |  |  | Select…
Is a Risk Analysis requested ? |  |  |  | Select…

## PlanèteSciences
La fiche de déclaration a-t-elle été revue ? | Sélectionner …
Les données ont-elles été saisies sur la page internet ? | Sélectionner …
Un retour au club a-t-il été fait ? | Sélectionner …
La fiche de définition a-t-elle été revue ? | Sélectionner …
Les données ont-elles été saisies sur la page internet ? | Sélectionner …
Un retour au club a-t-il été fait ? | Sélectionner …
La fiche technique a-t-elle été revue ? | Sélectionner …
Les données ont-elles été saisies sur la page internet ? | Sélectionner …
Un retour au club a-t-il été fait ? | Sélectionner …
La fiche de qualification a-t-elle été revue ? | Sélectionner …
Les données ont-elles été saisies sur la page internet ? | Sélectionner …
Un retour au club a-t-il été fait ? | Sélectionner …

## Source
Projet | Propulseur | Emetteur | Télémesure | Ralentisseur | Ejection | Structure | Lieu de mise en œuvre | Compétence | Viroles | Question | Impact dérog
Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner … | Sélectionner …
Fusée Expérimentale | Aucun | Aucun | Analogique - IRIG | Parachute | Ouverture transversale | La peau | Festiciels de Normandie | Mécanique | Virole Isard | Oui | Pas d'impact
Ballon Expérimental | Wapiti | Kiwi Millenium | Analogique - mode Kiwi Millenium* | Autre (précisez) | Porte latérale | La structure interne | Festiciels d'Altantique | Aérodynamique | Virole Chamois | Non | Peu d'impact
Minifusée Expérimentale | Cariacou | Autre (précisez) | Numérique |  | Autre (précisez) |  | Festiciels de Midi Pyrénnées | Patissier |  |  | Le projet est abandoné
Minifusée | Barasinga (Pro54-5G) | [5 empty] | Festiciels de Rhône Alpes | Electronique
| Orignal (Pro75-3G) | [5 empty] | Campagne Nationale* | Informatique
| Autre (précisez) | [5 empty] | Ballon (précisez)
Autre (précisez)
Project | Propellor | Transmitter | Telemetry | Recovery system | Ejection | Mecahnical Structure | Implementation site | Skill | Fin holder | Question | Dispensation consequence
Select… | Select… | Select… | Select… | Select… | Select… | Select… | Select… | Select… | Select… | Select… | Select…
Experimental rocket | None | None | Analog on IRIG | Parachute | Transverse partition | Skin | Festiciels in Normandy | Mechanics | Fin holder on Isard | Yes | No consequence
Experimental balloon | Wapiti | Kiwi Millenium | Analog on Kiwi Millenium* | Other (precise) | Lateral door | Internal structure | Festiciels in Atlantique | Aerodynamism | Fin holder on Chamois | No | Low consequence
Experimental minirocket | Cariacou | Other (precise) | Digital |  | Other (precise) |  | Festiciels in Midi Pyrenées | Cooking |  |  | Project cancelled
Minirocket | Barasinga (Pro54-5G) | [5 empty] | Festiciels in Rhône Alpes | Electronics
| Orignal (Pro75-3G) | [5 empty] | National campaign* | Coding
| Other (precise) | [5 empty] | Balloon (precise)
Other (precise)
ANNEE
2011-2012
DATES DE RETOUR | RETURN DATES
31 décembre 2011 | December 31st 2011
27 janvier 2012 | January 27th 2012
17 mars 2012 | March17th 2012
2 juin 2012 | June 2nd 2012